## Sheet1
|  | Project Name: | Risk Register
|  | Project Manager: | Carey Gobind
ID | Date Raised | Risk Description | Likelihood of the risk occuring | Impact if the risk occurs | Serverity(Rating based on impact & likelihood) | Owner(Person who will manage the risk) | Hazard Identification | Exposure Assessment | Mitigating action (Actions to mitigate the risk eg. Reduce the likelihood)2 | Risk after the contingent action taken
1 | 2024-07-01 | Extreme Heat | Medium | High | High | Aversen Govender/Jerome Mahalingham/Brandon De Lange | Increased frequency and intensity of heatwaves impacting driver health and vehicle performance. | Increased frequency and intensity of heatwaves impacting driver health and vehicle performance. | Investing in fuel-efficient trucks, improved cooling systems, and weather-resistant components. | Medium | Key
2 | 2024-07-01 | Severe Storms | High | High | High | Aversen Govender/Jerome Mahalingham/Brandon De Lange | Higher frequency and intensity of thunderstorms, hail, and high winds causing accidents and road damage. | Dependence on specific infrastructure (bridges, roads) susceptible to climate impacts. | Educating drivers on extreme weather driving techniques and safety protocols. | Medium | Low
3 | 2024-07-01 | Drought | High | High | High | Aversen Govender/Jerome Mahalingham/Brandon De Lange | Increased frequency for impacts on driver health and fatigue. | Reduced water availability for vehicle cooling systems and potential road degradation. | Planning routes to minimize exposure to high-risk weather areas. | Medium | Medium
4 | 2024-07-01 | Speeding | Medium | High | High | Aversen Govender/Jerome Mahalingham/Brandon De Lange | Increased accidents, incidents and fatality risk | Utilizing speed reports to compare operating speed limits during free flow against heavy flow traffic. Comparing speed reports, with crashes per vehicle against per vehicle km travelled to compare road segments. | Operations make immediate contact with driver once an alert is received. Driver is sent for refresher training on the possible consequences of speeding. | Low | High
5 | 2024-07-01 | Distracted Driving | Medium | High | High | Aversen Govender/Jerome Mahalingham/Brandon De Lange | Increased accidents, incidents and fatality risk | Tested drivers unknowingly with new tracking feature, for distractions | Training is provided on potential consequences, drivers are aware of consequences. | Low
6 | 2024-07-01 | Impaired Driving | Medium | High | High | Aversen Govender/Jerome Mahalingham/Brandon De Lange | Increased accidents, incidents and fatality risk | N/A | Daily breathalyzer tests with immediate dismissals for positive tests. | Medium
7 | 2024-07-01 | Fatigue | Low | High | High | Aversen Govender/Jerome Mahalingham/Brandon De Lange | Increased accidents, incidents and fatality risk | N/A | Rest breaks and driving hours are monitored daily. | Low
8 | 2024-07-01 | Bad Driving habits | Low | High | High | Aversen Govender/Jerome Mahalingham/Brandon De Lange | N/A | N/A | Driver behaviours are monitored continously | Low
9 | 2024-07-01 | Road Conditions | Medium | Medium | High | Aversen Govender/Jerome Mahalingham/Brandon De Lange | Worn-out tyres & blow outs | Dependence on specific infrastructure (bridges, roads) susceptible to climate impacts. | Alternate routes with better infrastructure and constant tyre checks. | Low
10 | 2024-07-01 | Wildlife crossing | Low | Medium | High | Aversen Govender/Jerome Mahalingham/Brandon De Lange | N/A | Dependant on area and region. | Drivers are trained to always be travelling carefully at a safe distance, which allows ample time to react properly. | Low